## Sheet1
|  | Work Log |  | Acc hours | 122
Date | Time spent (hours) | Work Description | Comments
2010-04-19 | 3 | Project Overview & Scope | Define system boundaries, features, users
2010-04-20 | 3 | Project Overview & Scope
2010-04-21 | 2.5 | Project Overview & Problem/Opportunity Analysis | Define opportunity for system and problems that may arise
2010-04-22 | 3.5 | Requirements Analysis | List Requirements and Priorities
2010-04-23 | 2 | Requirements Analysis & Logical Design | Creation of use cases
2010-04-26 | 2 | Requirements Analysis & Logical Design | Creation of use cases
2010-04-29 | 2 | Logical Design | Context Diagram
2010-04-30 | 2 | Logical Design | Context Diagram
2010-05-03 | 3 | Logical Design | DFD
2010-05-04 | 3 | Physical Design | ERD and Interface Design
2010-05-06 | 3.5 | Physical Design | ERD,Site Map and Interface Design
2010-05-07 | 3 | Logical Design & Physical Design | DFD
2010-05-11 | 1 | Logical Design & Physical Design | Logical ERD Complete
2010-05-12 | 2 | Physical Design | Physical ERD
2010-05-13 | 0 | Exams
2010-05-14 | 0 | Exams
2010-05-17 | 3 | Learning C#
2010-05-18 | 3 | Learning C#
2010-05-20 | 5 | Learning C#, ASP.Net
2010-05-23 | 2 | Learning C#, ASP.Net
2010-05-26 | 3.5 | Coding + Multimedia design | User Interface design, skeleton of site using CSS
2010-05-27 | 12 | Coding | Login form, trying to get cookies working properly
2010-05-28 | 4 | Coding | Login form, trying to get cookies working properly
2010-05-29 | 5 | Coding | Login form, succeded getting cookies working properly
2010-05-30 | 10 | Coding | Roles, login form correct redirection of authenticated users
2010-05-30 | 4 | Coding(2) + Internet Research (2) | working on logout and user roles, authetication and access
2010-06-01 | 5 | Coding(4.5) + Internet Reseach (0.5) | Logout Working, Clearing web cookie, reconfigured database for users and roles, implementing new table in database
2010-06-02 | 8 | Coding | Creating Registration Forms and Database Relations | 100 hours
2010-06-03 | 0 | Exams
2010-06-04 | 0 | Exams
2010-06-05 | 7 | Coding | Create registration forms validation and submit registration form to database creating a new user
2010-06-06 | 10 | Coding | Create registration forms validation and submit registration form to database creating a new user
2010-06-07 | 5 | Coding | change password, registration form
2010-06-08 |  |  | Basic User controls, company host advertisemet
2010-06-09
2010-06-10
2010-06-11
2010-06-12
2010-06-13
2010-06-14
2010-06-15
2010-06-16
2010-06-17
2010-06-18
2010-06-19
2010-06-20
2010-06-21
2010-06-22
2010-06-23
2010-06-24
2010-06-25
2010-06-26
2010-06-27
2010-06-28
2010-06-29
2010-06-30
2010-07-01
2010-07-02
2010-07-03
2010-07-04
2010-07-05
2010-07-06
2010-07-07
2010-07-08
2010-07-09
2010-07-10
2010-07-11
2010-07-12
2010-07-13
2010-07-14
2010-07-15
2010-07-16
2010-07-17
2010-07-18
2010-07-19
2010-07-20
2010-07-21
2010-07-22
2010-07-23 |  | Presentation Day